## Sprint 1 Backlog
Story # | Sprint Backlog Item | Task # | Volunteer | update sprint backlog | Initial Effort Estimate (hrs) | New Estimates of Effort remaining at end of | [5 empty] | Status
[6 empty] | Day1 | Day2 | Day3 | Day4 | Day5 | Day6
US001 | As a customer-account executive /cashier / teller I want to be able to log in the bank website with my user ID and password So that I carry out my transactions | Task 1 | Amar | Create a customer form and header and footer of project | 6 | 6 | 0 | 0 | 0 | 0 | 0 | Closed
|  | Task 2 | Mohit | Home page login backend | 5 | 5 | 0 | 0 | 0 | 0 | 0 | Closed
|  | Task 3 | Saket | Design and create the DB fields | 5 | 5 | 0 | 0 | 0 | 0 | 0 | Closed
|  | Task 4 | Shreyas | Update sprint backlog | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Closed
|  | Task 5 | Athar | Updating JIRA and DOD | 2 | 2 | 0 | 0 | 0 | 0 | 0 | Closed
US002 | As a customer-account executive I want to be able to capture new customer information So that I can create a new customer in the system | Task 1 | Amar | Front End For capturing customer information | 5 | 5 | 0 | 0 | 0 | 0 | 0 | Closed
|  | Task 2 | Mohit | Create customer backend | 6 | 6 | 0 | 0 | 0 | 0 | 0 | Closed
|  | Task 3 | Saket | Creating the Dao and Pojo classes | 5 | 5 | 0 |  | 0 | 0 | 0 | Closed
|  | Task 4 | Shreyas | Update sprint backlog | 2 | 2 | 0 | 0 | 0 | 0 | 0 | Closed
|  | Task 5 | Athar | Updating JIRA and DOD | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Closed
US003 | As a customer-account executive I want to be able to edit existing customer information So that I can store the updated customer information in the system | Task 1 | Amar | Front End for updating customer inforation | 6 | 6 | 6 | 0 | 0 | 0 | 0 | Closed
|  | Task 2 | Mohit | update customer form | 5 | 5 | 5 | 0 | 0 | 0 | 0 | Closed
|  | Task 3 | Saket | update customer backend | 5 | 5 | 5 | 0 | 0 | 0 | 0 | Closed
|  | Task 4 | Shreyas | Update sprint backlog | 1 | 1 | 1 | 0 | 0 | 0 | 0 | Closed
|  | Task 5 | Athar | Updating JIRA and DOD | 2 | 2 | 2 | 0 | 0 | 0 | 0 | Closed
US004 | As a customer-account executive I want to be able to delete existing customer from system | Task 1 | Amar | Front end for deleting | 5 | 5 | 5 | 0 | 0 | 0 | 0 | Closed
|  | Task 2 | Mohit | delete customer controller mapping | 5 | 5 | 5 | 0 | 0 | 0 | 0 | Closed
|  | Task 3 | Saket | delete customer from DAO | 5 | 5 | 5 | 0 | 0 | 0 | 0 | Closed
|  | Task 4 | Shreyas | update sprint backlog | 2 | 2 | 2 | 0 | 0 | 0 | 0 | Closed
|  | Task 5 | Athar | Updating JIRA and DOD | 1 | 1 | 1 | 0 | 0 | 0 | 0 | Closed
US005 | As a customer-account executive I want to be able to view the status of all the customers of the bank | Task 1 | Amar | front end for viewing status | 5 | 5 | 5 | 0 | 0 | 0 | 0 | Closed
|  | Task 2 | Mohit | customer status backend | 6 | 6 | 6 | 0 | 0 | 0 | 0 | Closed
|  | Task 3 | Saket | updating customer table,DAO classes | 4 | 4 | 4 | 0 | 0 | 0 | 0 | Closed
|  | Task 4 | Shreyas | update sprint backlog | 1 | 1 | 1 | 0 | 0 | 0 | 0 | Closed
|  | Task 5 | Athar | Updating the POJO class | 2 | 2 | 2 | 0 | 0 | 0 | 0 | Closed
US006 | As a customer-account executive I want to be able to capture account details So that I can create a new bank account for an existing customer | Task 1 | Amar | front end for craeting an account | 5 | 5 | 5 | 5 | 0 | 0 | 0 | Closed
|  | Task 2 | Mohit | Create account backend | 5 | 5 | 5 | 5 | 0 | 0 | 0 | Closed
|  | Task 3 | Saket | Create account table, pojo and dao classes | 4 | 4 | 4 | 4 | 0 | 0 | 0 | Closed
|  | Task 4 | Shreyas | update sprint backlog | 2 | 2 | 2 | 2 | 0 | 0 | 0 | Closed
|  | Task 5 | Athar | Updating JIRA and DOD | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Closed
US007 | As a customer-account executive I want to be able to delete an account of an existing customer | Task 1 | Amar | front end for deleting account | 6 | 6 | 6 | 6 | 0 | 0 | 0 | Closed
|  | Task 2 | Mohit | delete account backend | 5 | 5 | 5 | 5 | 0 | 0 | 0 | Closed
|  | Task 3 | Saket | delete account form from dao | 4 | 4 | 4 | 4 | 0 | 0 | 0 | Closed
|  | Task 4 | Shreyas | update sprint backlog | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Closed
|  | Task 5 | Athar | Updating JIRA and DOD | 2 | 2 | 2 | 2 | 0 | 0 | 0 | Closed
US008 | As a customer-account executive I want to be able to view the status of all the accounts of the bank | Task 1 | Amar | account status frontend | 5 | 5 | 5 | 5 | 0 | 0 | 0 | Closed
|  | Task 2 | Mohit | account status mapping | 5 | 5 | 5 | 5 | 0 | 0 | 0 | Closed
|  | Task 3 | Saket | account status backend | 4 | 4 | 4 | 4 | 0 | 0 | 0 | Closed
|  | Task 4 | Shreyas | update sprint backlog | 2 | 2 | 2 | 2 | 0 | 0 | 0 | Closed
|  | Task 5 | Athar | updating dao | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Closed
USOO9 | As a customer-account executive I want to be able to search for a customer So that I am able to view the details | Task 1 | Amar | front end for search customer | 5 | 5 | 5 | 5 | 5 | 0 | 0 | Closed
|  | Task 2 | Mohit | backend for search customer | 5 | 5 | 5 | 5 | 5 | 0 | 0 | Closed
|  | Task 3 | Saket | backend for search customer | 3 | 3 | 3 | 3 | 3 | 0 | 0 | Closed
|  | Task 4 | Shreyas | update sprint backlog | 1 | 1 | 1 | 1 | 1 | 0 | 0 | Closed
|  | Task 5 | Athar | frontend for displaying view details of customer | 2 | 2 | 2 | 2 | 2 | 0 | 0 | Closed
US010 | As a Cashier/ Teller I want to be able to search for a bank account So that I am able to view the details | Task 1 | Amar | front end for search account | 5 | 5 | 5 | 5 | 5 | 0 | 0 | Closed
|  | Task 2 | Mohit | backend for search account | 5 | 5 | 5 | 5 | 5 | 0 | 0 | Closed
|  | Task 3 | Saket | backend for search account | 3 | 3 | 3 | 3 | 3 | 0 | 0 | Closed
|  | Task 4 | Shreyas | update sprint backlog | 2 | 2 | 2 | 2 | 2 | 0 | 0 | Closed
|  | Task 5 | Athar | Updating JIRA and DOD | 1 | 1 | 1 | 1 | 1 | 0 | 0 | Closed
US011 | As a Cashier/ Teller I want to be able to deposit money into a customer's account So that I am able to service the customer's request | Task 1 | Amar | deposit page front end | 5 | 5 | 5 | 5 | 5 | 0 | 0 | Closed
|  | Task 2 | Mohit | deposit business logic and backend | 5 | 5 | 5 | 5 | 5 | 0 | 0 | Closed
|  | Task 3 | Saket | update queries on account attributes | 3 | 3 | 3 | 3 | 3 | 0 | 0 | Closed
|  | Task 4 | Shreyas | update sprint backlog | 1 | 1 | 1 | 1 | 1 | 0 | 0 | Closed
|  | Task 5 | Athar | Updating JIRA and DOD | 2 | 2 | 2 | 2 | 2 | 0 | 0 | Closed
US012 | As a Cashier/ Teller I want to be able to withdraw money from a customer's account So that I am able to service the customer's request | Task 1 | Amar | withdrawal page frontend | 5 | 5 | 5 | 5 | 5 | 0 | 0 | Closed
|  | Task 2 | Mohit | withdrawal business logic and backend | 4 | 4 | 4 | 4 | 4 | 0 | 0 | Closed
|  | Task 3 | Saket | update queries on account attributes | 3 | 3 | 3 | 3 | 3 | 0 | 0 | Closed
|  | Task 4 | Shreyas | update sprint backlog | 2 | 2 | 2 | 2 | 2 | 0 | 0 | Closed
|  | Task 5 | Athar | Updating JIRA and DOD | 1 | 1 | 1 | 1 | 1 | 0 | 0 | Closed
US013 | As a Cashier/ Teller I want to be able to transfer money from a customer's account So that I am able to service the customer's request | Task 1 | Amar | transfer money frontend | 5 | 5 | 5 | 5 | 5 | 5 | 0 | Closed
|  | Task 2 | Mohit | transfer money business logic and backend | 4 | 4 | 4 | 4 | 4 | 4 | 0 | Closed
|  | Task 3 | Saket | update queries on account attributes | 2 | 2 | 2 | 2 | 2 | 2 | 0 | Closed
|  | Task 4 | Shreyas | update sprint backlog | 2 | 2 | 2 | 2 | 2 | 2 | 0 | Closed
|  | Task 5 | Athar | Updating JIRA and DOD | 1 | 1 | 1 | 1 | 1 | 1 | 0 | Closed
US014 | As a Cashier/ Teller I want to be able to print an account statement So that I am able to service the customer's request | Task 1 | Amar | Design print feature for customer service front end | 4 | 4 | 4 | 4 | 4 | 4 | 0 | Closed
|  | Task 2 | Mohit | Code for download Account statement in pdf format | 3 | 3 | 3 | 3 | 3 | 3 | 0 | Closed
|  | Task 3 | Saket | selection of desired attributes in the printable document | 2 | 2 | 2 | 2 | 2 | 2 | 0 | Closed
|  | Task 4 | Shreyas | update sprint backlog | 1 | 1 | 1 | 1 | 1 | 1 | 0 | Closed
|  | Task 5 | Athar | frontend for view details of account statement | 2 | 2 | 2 | 2 | 2 | 2 | 0 | Closed
|  |  |  | Total | 234 | 234 | 196 | 141 | 89 | 26 | 0

## Sprint 1 Burndown Chart
Day0 | Day1 | Day2 | Day3 | Day4 | Day5 | Day6
235 | 234 | 197 | 142 | 90 | 27 | 0
234 | 195 | 156 | 117 | 78 | 39 | 0